## Defect Tracking Log
DEFECT TRACKING LOG
Project Name
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 05.01.2026. | Ajla Stranjak | 1. Open web browser (e.g. Google Chrome). 2. Open www.olx.ba web page on web browser. 3. Homepage is displayed. 4. Locate the search bar. 5. Enter "brusilica" in the search bar. 7. Press "Enter" to perform the search. 8. Verify that search results for "brusilica" are displayed. 9. Observe that one of the listed ads for "brusilica" is marked as posted "prije 25 minuta". 10. Open the dropdown filter "Filteri oglasa". 11. Select the filter option "Zadnja 24h". 12. Verify the updated search results. EXPECTED RESULT: All ads posted within the last 24 hours, including the ad posted "prije 25 minuta", should be displayed in the filtered search results. ACTUAL RESULT: The ad for "brusilica" posted "prije 25 minuta" is not displayed in the search results after applying the "Zadnja 24h" filter. | [6 empty] | New |  |  |  |  | New
2 | 05.01.2026. | Asima Halilagić | 1. Open web browser (e.g. Google Chrome). 2. Open www.olx.ba web page on web browser. 3. Homepage is displayed. 4. Locate the search bar. 5. Enter "macka" in the search bar. 6. Press "Enter" to perform the search. 7. Verify that total number of search results is displayed (Total results: 5995). 8. Open the dropdown filter "Sortiraj". 9. Select the filter option "Najviša". 10. Verify that search results are sorted correctly and total number of results is displayed (Total results now show 5224). EXPECTED RESULT: Total number of search results should remain consistent (5995) regardless of sorting/filter applied, only the order of items should change. ACTUAL RESULT: Total number of results decreases from 5995 to 5224 after applying "Najviša" filter. | [6 empty] | New |  |  |  |  | New
3 | 05.01.2025. | Amina Fazlić | 1. Open the web browser (e.g. Google Chrome). 2. Open www.olx.ba web page on web browser. 3. Log in with valid user credentials. 4. Click on the menu icon. 5. Select "Postavke" from the menu. 6. Click on "Korisničke informacije". 7. Click on the input field labeled “Broj telefona (broj unijeti u formatu +3876xxxxxxx)”. 8. Enter an invalid phone number: +444 4444 444 44 4. 9.Click on the "Spasi izmjene" button. ACTUAL RESULT: No validation error message is displayed for the invalid phone number format. No success or error notification is shown. After manually refreshing the page, the phone number is not saved. EXPECTED RESULT: An error message should be displayed indicating that the phone number must be entered in the correct format. | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 05.01.2026. | Asima Halilagić | 1. Open web browser (e.g. Google Chrome). 2. Open www.olx.ba web page on web browser. 3. Homepage is displayed. 4. Locate the search bar. 5. Enter "macka" in the search bar. 6. Press "Enter" to perform the search. 7. Verify that search results include ads with price set as "Na upit". 8. Open the dropdown filter "Sortiraj". 9. Select the filter option "Najviša". EXPECTED RESULT: Listings with price set as "Na upit" should still be included in the results. ACTUAL RESULT: Listings with price set as "Na upit" are excluded from search results when sorting by price is applied. | [6 empty] | New
5 | 05.01.2026. | Ajla Stranjak | 1. Open web browser (e.g. Google Chrome). 2. Open www.olx.ba web page on web browser. 3. Homepage is displayed. 4. Locate the search bar. 5. Enter "bengalska macka" in the search bar. 7. Press "Enter" to perform the search. 8. Verify that search results for "bengalska macka" are displayed. 9. Observe that one of the listed ads for "bengalska macka" is marked as posted "prije 20 dana". 10. Open the dropdown filter "Filteri oglasa". 11. Select the filter option "Zadnji mjesec". 12. Verify the updated search results. EXPECTED RESULT: All ads posted within the last 30 days, including the ad posted "prije 20 dana", should be displayed in the filtered search results. ACTUAL RESULT: The ad for "bengalska macka" posted "prije 20 dana" is not displayed in the search results after applying the "Zadnji mjesec" filter. | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
[17 empty] | Closing | Development
Testing
Documentation and Training
Deployment
Post-Deployment
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).